## Hardware
Requirement | Comment | Priority | Status
2 OLTs per variant
Edgecore (BCM) OLT (2nd HW variant)
9 ONTs (SOC preferred)
-48V DC-powered OLT
CO deployable HW (NEBS, TP-762xx, etc.)
4 OLT optics modules per variant
ODN (optical crossconnect, 4 splitters)
TOR (need to confirm if redundant equipment and -48V DC power requirements are applicable)
Non-EdgeCore Only
EdgeCore
ALL
Not OLT

## Software & Integration
# | Requirement | Category | Story | Priority | Priority H1>H2>H3 | Comment/Reasoning from Reviews | New | VOLTHA Epic | VOLTHA Story | VOLTHA | ONOS Epic | ONOS Story | ONOS | VOLTHA 1.0 | VOLTHA 1.0 Plus | Shawn Notes | Jira Status | OLT Dependency
1 | 4.7 General Requirements
2 | 4.7.2 Software Images for Operator Production Network
3 | • Download images without access to internet | SW & Image Management |  | Gating | H1 |  | Y | VOL-6 | VOL-6 | Y |  |  | Y | Y |  | Done | Done | VOLTHA
4 | 4.7.2 Software Images for Operator Production Network
5 | • Version control of SW images | SW & Image Management |  | H | H1 | Latest only. Start fron V1 | Y | VOL-6 | VOL-6 | Y |  |  | Y | Y |  | Done | Done | VOLTHA
6 | 4.7.3 Restartable in Isolation
7 | • Restart images without internet access | SW & Image Management |  | Gating | H1 |  | Y | VOL-6 | VOL-6 | Y |  |  | Y | Y |  | Done | Done | VOLTHA
8 | 4.7.4 Alarm and Condition Configuration and Reporting
8 | • Configuration of Severity (Split 1 Req) | Alarms |  | M | M |  | Y | ? | ? | Y |  |  | Y | N | TBD | The ? Need to be updated
9 | • Configuration Alarm Suppression, Alarm ACK, Alarm clearing | Alarms |  | M | M |  | Y | ? | ? | Y |  |  | Y | N | TBD
10 | 4.7.5 Backup and Restore
11 | • Config trasferrable to detachable physical medim (Or FTP) | SW & Image Management |  | H | H3 | Very important requirement but same rationale as 13. "Do things ringt the first time". A backup is needed to typically re-ingest it back. Is it ok and will it suffice with a script? | Y | VOL-8 | VOL-8 | Y |  |  | Y | Y |  | Must have for the release |  | VOLTHA
12 | • Ingesting an existing backup configuration file | SW & Image Management |  | M | M | Very important requirement however iIngesting a new backup file is for ease when turning up new nodes. It would still need some edits if for e.g. the ONU SNs need to be changed. Can the same be achieved via re-running the config script file? Note that we may want to move towards target-arch for backup-restore(i.e external database & NC/Y data-store). So also looking from "do things right the first time" point of view | Y | VOL-8 | VOL-8 | Y |  |  | Y | N | Y | Must have for the release
13 | 4.7.6 PON Registration Method
14 | • Support Registration Method A (ONU Serial number) | Pon Management |  | H | H1 |  | Y | VOL-7 | ? | Y |  |  | N | Y |  | adpater dependency |  | ALL OLTs
15 | • Auto Registration of ONUs (with configurable allow/deny) | Pon Management |  | M | M | To remobe the hardcode | Y | VOL-7 | VOL-52 | Y |  |  | N | N | TBD | Remove the hardcoded method |  | ALL OLTs
16 | 4.7.7 Software/Firmware Upgrade Strategy and Capability
17 | • In Service SW modification | SW & Image Management |  | H | H3 |  | Y | VOL-133 | VOL-105 | Y |  |  | Y | Y |  | Major upgrade vs patch. For Ph3 SW modification |  | Non-EdgeCore Only
18 | • Retain configuration over upgrades & Restore from saved database over an upgrade | SW & Image Management |  | H | H3 |  | Y | VOL-8 | VOL-8 | Y |  |  | Y | Y |  | Patch update need to retain the DB. It may be addressed in doc or process (TBD). List the ones can cause DB lost |  | ALL OLTs
19 | 4.7.8 High-Availability
20 | • Clustering of VOLTHA containers and VOLTHA | High-Availability |  | H | H2 | Is quite important but proposingH2 just relative of others. | Y | VOL-5 | VOL-5 | Y |  |  | Y | Y |  | As long as Frame work works. |  | Not OLT
21 | 4.8 Commissioning Requirements
22 | • Describe the procedure and criteria for determining that a new deployment of equipment and software have been properly installed, and are fully functional | SW & Image Management |  | H | H1 |  | Y | ? | ? | Y |  |  | Y | Y |  | Procedure |  | ALL OLTs
22 | 5.1 Configuration
23 | • Provisioning via NETCONF | NBI |  | M | M |  | Y | VOL-9 | VOL-9 | Y |  |  | Y | Y |  |  |  | ALL OLTs
24 | • Pre-provision a new ONT from Netconf and/or vOLT CLI | Pon Management |  | H | H1 |  | Y | VOL-7 | ? | Y |  |  | N | Y |  |  |  | ALL OLTs
24 | • Provision services (uni-cast) | Service Management |  | H | H1 |  | Y | N/A | N/A | N |  |  | Y | Y |  | No MultiCase for EdgeCore |  | ALL OLTs
25 | • Provision services (multi-cast) | Service Management |  | H | H1 |  | Y | N/A | N/A | N |  |  | Y | Y |  | No MultiCase for EdgeCore |  | Non-EdgeCore Only
25 | • Provision services automatically | Pon Management |  | L | L |  | Y | N/A | N/A | N |  |  | Y |  |  | Remove
26 | • Delete ONT | Device Management |  | H | H1 |  | Y | VOL-7 | VOL-7 | Y |  |  | N | Y |  |  | VOL-93 | ALL OLTs
27 | • Delete services | Service Management |  | H | H1 |  | Y | N/A | N/A | N |  |  | Y | Y |  | Doesn ONOS Epic/Story need to add |  | ALL OLTs
27 | • Provision LAG group on ToR Switch | Entity Management |  | N/A | H1 | 7450 probably expects Single Member LAG [but ToR is not managedby VOLTHA] | Y | N/A | N/A | N |  |  | ? | N |  | Not VOLTHA or ONOS |  | Stretch Goal for all OLTs
28 | • Provision LAG group on OLT More dicussion - Current software doesn't support it . | Entity Management |  | H -> L | H3 | The OLT <-> ToR link is within the rack and mostly using a DAC. Is this critical for Field Trial? If critical, Would static LAG suffice? Yes [for FT Staticmaybe ok. But we need to be able to configure LAG toward on OLT NNI] Or Manual | Y | ? | ? | ? |  |  | N | N | Y | The ? Need to be updated Maybe 2 ToR switches and the OLT has separate link to each ToR. LAG will mostly be used as addition NNI BW. Single member link to start for 2017 is ok |  | Stretch Goal for all OLTs
28 | 5.2 Scalability
29 | • Provision multiple ONTs on a PON | Scalability |  | H | H1 |  | Y | VOL-7 | ? | Y |  |  | N | Y |  |  |  | ALL OLTs
30 | • Provision multiple ONTs/Services on a PON – Verify ONOS is capable of processing multiple EAP, DHCP and IGMP proxy/snooping functions. | Scalability |  | H | H1 |  | Y | N/A | N/A | N |  |  | Y | Y |  | ONOS |  | ALL OLTs
30 | • Establish 4-6 simultaneous streams per ONT – Verify no packet loss | Scalability |  | H | H1 |  | N | N/A | N/A | N |  |  | N | N/A |  | Operator will test for sure No additional effort for VOLTHA | VOL-114 | Non-EdgeCore Only
31 | • At least 64 ONTs, we want to see when all ONTs/RGs come to service if ONOS can handle storm of EAP/DHCP request (Applicable to Ph3/Ph4?) | Scalability |  | L |  |  | Y | N/A | N/A | N |  |  | Y | N |  |  |  | Stretch Goal for all OLTs
32 | 5.3 Resiliency
33 | • Verify vOLT instantiation/instance can be regenerated from a complete deletion situation (Legacy database backup/restore test case). | Resiliency |  | H | H2 | Same as 13 | Y | VOL-8 | VOL-8 | Y |  |  | Y | Y |  | Test case of the backup and restore
34 | • Reboot vOLT – verify forwarding table resiliency | Resiliency |  | H | H1 |  | N | N/A | N/A | N |  |  | N | Y |  | Why N/A on VOLTHA? | VOL-200 | ALL OLTs
35 | • Remove connectivity between vOLT and ONOS – ensure configurations and services are restored | Resiliency |  | H | H1 |  | N | N/A | N/A | N |  |  | N | Y |  | Operator will test for sure |  | ALL OLTs
36 | • Leaf switch reboot, ONOS/VOLT reboot/restart/disconnect when service is running, observe service backup | Resiliency |  | H | H1 |  | N | N/A | N/A | N |  |  | Y | Y |  | Same as line 41? |  | ALL OLTs
37 | • STC sends unknown unicast to test ONOS server process of flash of traffic | Resiliency |  | L |  |  | Y | N/A | N/A | N |  |  | Y |  |  |  |  | ALL OLTs
38 | • FIT – Fault Insertion Tests () | Resiliency |  | M | M | Reponse from Operator on FIT "FIT – Faults are not deterministic at this time, so assume any non-destructive h/w tests and any s/w tests are fair game (e.g., open fibers, loss of power, cored processes, filesystem full, ONU software mismatch , Connectivity---servers with OLTs, OLT with ONU, LOS, RDI, LOA, Facility---HW fail, ONT dying gasp, VOLT/ONOS Docker process failed or stopped , Service level---radius, DHCP, IGMP, etc.). This list is not intended to be exhaustive." | Y | ? | ? | Y |  |  | Y |  |  | Test case of the backup and restore. Notr developmemt
39 | 5.4 QoS / Service-Level Items
40 | • Provision multiple ONTs on a PON – Verify T-CONT (CBR, ABR functions) configuration | Onu Management |  | H | H2 |  | Y | Additional Story?? | Additional Story?? | Y |  |  | N | Y |  | Agree BAL Cannot provide it now we havae other ONT types and Other OLT doesn't use BAL, right? H2 now, but framework is in core and should be established first. BAL - also |  | ALL OLTs
41 | • Provision multiple ONTs on a PON – Verify T-CONT (CBR, ABR functions), p-bit processes and service profiles are properly managed by queues when congested. | Onu Management |  | H | H2 |  | Y | Additional Story?? | Additional Story?? | N |  |  | Y | Stretch | Y | H/W VOLTHA for config YANG QoS needs to be in place (prefer). Pbit on rG should be ok. Nokia submit ONOS mapping already in 1.10 |  | ALL OLTs
42 | • Verify maximum throughput capability of data service – 1G and 10G | Throughput |  | H | H1 |  | N | N/A | N/A | N |  |  | N | N/A | N/A | Data Plane req |  | ALL OLTs
43 | • QoS testing – Test VLAN priority tagging. Saturate an ONT with traffic of different priorities and confirm they are discarded accordingly | QoS |  | H | H1 |  | N | N/A | N/A | N |  |  | N | Y |  | Data Plane req |  | ALL OLTs
44 | • Perform standard frame size tests (64, 128, 256, 512, 1025, etc.) | Throughput |  | H | H1 |  | N | N/A | N/A | N |  |  | N | Y |  | Data Plane req |  | ALL OLTs
45 | • OLT need to do downstream traffic shaping (Configuration of DS queues/schedulers?) | QoS |  | M | M | Configuration of DS queues/schedulers is important but relatively low prioirty when compared to other H items. | Y | ? | ? | Y |  |  | Y | N | Y | Model needs to be in place. Can we have a story in place for exploration? Further QoS story to create |  | Stretch Goal
46 | 5.5 Performance Monitoring
47 | • Verify PON bandwidth utilization status – verify ability to see available bandwidth. | Pon Management |  | L | L | For the field trial with 9 ONUs, it is unlikely that the PON utilization is a concern | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | ALL OLTs
48 | • Verify ONT optical power levels and distance from OLT can be seen. | Onu Management |  | M |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
49 | • Verify ability to query inventory of how many ONTs are in service. | Pon Management |  | M |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
50 | • Verify ability to acquire RG authentication status. | Control Plane |  | M |  |  | N | N/A | N/A | N |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
51 | • Verify ability to query CPU, I/O and memory status. | System Management |  | L |  |  | Y | ? | ? | Y |  |  | Y | Stretch | Y |  |  | Non-EdgeCore OLT
52 | • Verify ability to query NNI utilization. | Device Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
53 | 5.6 Facility Management
54 | • Verify system’s ability to detect new ONTs | Onu Management |  | Gating | Gating |  | N | in progress | in progress | Y |  |  | N | Y |  | The ? Need to be updated |  | ALL OLTs
55 | • Verify system’s ability to see ONTs ranged (and not activated). | Onu Management |  | M |  |  | N | ? | ? | Y |  |  | N | Stretch | Y |  |  | ALL OLTs
56 | • Verify system’s ability to detect/Display IS and OOS ONT service states. | Device Management |  | H | H1 |  | Y | ? | Story | Y |  |  | Y | Y |  | The ? Need to be updated Available as part of 61? VOLTHA CLI (Operational State support on the Device Management) |  | ALL OLTs
57 | • Verify ability to console/login to OLT HW for status check. |  |  | M |  |  | N | ? | ? | Y |  |  | N |  |  |  |  | ALL OLTs
58 | 5.7 Alarms, States, Conditions
59 | 5.7.1 Retrieve Provisioned PON Parameters
60 | • IS, OOS (both state and configured) | Device Management |  | H | H1 |  | Y | ? | ? | Y |  |  | N | Y |  | The ? Need to be updated |  | ALL OLTs
61 | • vOLT instance association | Device Management |  | H | H1 |  | N | Done | Done | Y |  |  | N | Y |  |  |  | ALL OLTs
62 | • BER time measurement period that determines SD condition | Pon Management |  | M |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
63 | • BER threshold used to establish SD condition | Pon Management |  | M |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
64 | • BER threshold used to establish SF condition | Pon Management |  | M |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
65 | • FEC enabled/disabled | Onu Management |  | H | H1 | Disabling FEC is not recommended when running 10G | N | in progress | in progress | Y |  |  | N | Stretch | Y | Core will support depends on the HW |  | Non-EdgeCore OLT
66 | • Distance of closest ONT | Pon Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
67 | • Maximum differential logical reach on PON | Pon Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
68 | • Rogue ONT test | Pon Management | Unknown | L |  |  | Y | ? | ? | Y | Unknown | Unknown | N | Stretch | Y | Reflect action |  | Non-EdgeCore OLT
69 | • Upstream traffic threshold | Pon Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
70 | • Downstream traffic threshold | Pon Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
71 | • PON label/description | Pon Management |  | L |  |  | N | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
72 | • Multicast encryption enabled/disabled (de-scoped) | Pon Management | Unknown | L | L | not required for Phase-3 | Y | N/A | N/A | Y | Unknown | Unknown | N
73 | 5.7.2 Retrieve operational PON parameters
74 | • Ranged ONT numbers/identifiers | Pon Management |  | M |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y | Able to associate the ONT SN to the PON port |  | Non-EdgeCore OLT
75 | • IGMP – number of queries, drops, etc. and associated addresses. | Control Plane |  | L | L | Relatively low prioriry when compared to other M items | Y | N/A | N/A | N |  |  | Y | Stretch | Y | Part of the IGMP snooping |  | Non-EdgeCore OLT
76 | • BEC DS | Pon Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
77 | • BEC US | Pon Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
78 | • ONT ranging condition | Pon Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
79 | 5.7.3 Retrieve Provisioned ONT Parameters
80 | • IS, OOS (both state and configured) | Device Management |  | H | H1 |  | Y | ? | ? | Y |  |  | N | Y |  | The ? Need to be updated |  | ALL OLT
81 | • Ethernet Interface (UNI) – link configuration (i.e. 1000BTFULLDPLX), link admin state (UP/DOWN) | Onu Management |  | H | H1 | 1000 Full Duplex config is not H IMHO | Y | ? | ? | Y |  |  | N | Y |  | Auto as default |  | ALL OLT
82 | • 802.1x authentication – auto/forcedauth/forcedunauth, server timeout, supplicant timeout, maximum requests, reauthorization enable/disable, reauthorization timeout | Control Plane |  | L | L | Considering this low as this is for tuning to N/W latencies, responsiveness etc | Y | N/A | N/A | N |  |  | Y |  |  |  |  | ALL OLT
83 | • PAE port enable/disable | Control Plane |  | H | H1 |  | Y |  |  | N |  |  | Y | Y |  | ONOS Flow Rule not there is there. No support today; (Check with David B) |  | ALL OLT
84 | • Battery backup (present/not present) (de-scoped) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N
85 | • BER accumulation interval | Onu Management |  | L |  |  | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y
86 | • NTP information (de-scoped) | Onu Management |  | L | L |  | Y | N/A | N/A | Y |  |  | N
87 | • Description | Onu Management |  | M |  |  | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y
88 | • Part number | Onu Management |  | M |  |  | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y
89 | • Serial number | Onu Management |  | H | H1 |  | Y | VOL-7 | VOL-95 | Y |  |  | N | Y
90 | • Location Identifier | Onu Management |  | M | M | Is this critical for Field trial? [Ying - OK- does 802.1x need it?] | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y
91 | • Planned SW version | Onu Management |  | H | H2 | Relatively lower when compared to other H | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch
92 | • FEC (enabled/disabled) | Onu Management |  | M | H1 | Disabling FEC is not recommended when running 10G | N | ? | ? | Y |  |  | N | Stretch | Y | Default should set to enable.
93 | • Power shedding profile (de-scoped) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N
94 | • Optical measurements (RSSI) | Onu Management |  | M |  |  | Y | ? | ? | Y |  |  | N |  | Y
95 | • Active SW | Device Management |  | H | H2 | Relatively lower when compared to other H | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y | What is the mechanism to see the running and 2ndary on the ONT |  | ALL OLT
96 | • Passive SW | Device Management |  | H | H2 | Relatively lower when compared to other H | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y |  |  | ALL OLT
97 | • Vendor ID | Onu Management |  | M | M | Vendor Id can be retrieved from SN [OK] | Y | VOL-7 | VOL-95 | Y |  |  | N | Y |  |  |  | ALL OLT
98 | • Number of slots | Onu Management |  | M | M |  | Y | VOL-7 | VOL-95 | Y |  |  | N | Y |  |  |  | ALL OLT
99 | • Number of T-CONTS | Onu Management |  | M | M | It is not critcal since for field trial, only 1 TCONT and 4 qs are used per ONT. It is more a informational item | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y |  |  | ALL OLT
100 | • Number of traffic schedulers | Onu Management |  | M | M | It is not critcal since for field trial, only 1 TCONT and 4 qs are used per ONT. It is more a informational item | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y |  |  | ALL OLT
101 | • Number of priority queues | Onu Management |  | M | M | It is not critcal since for field trial, only 1 TCONT and 4 qs are used per ONT. It is more a informational item | Y | VOL-7 | VOL-95 | Y |  |  | N | Stretch | Y |  |  | ALL OLT
102 | • Upstream policing (on/off) (de-scoped?) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N | Stretch | Y |  |  | ALL OLT
103 | • AES (enable/disable) | Onu Management | descope | H | H2 | Relatively lower when compared to other H | Y | ? | ? | Y |  |  | N | Stretch | Y | The ? Need to be updated |  | ALL OLT
104 | • CVLAN translation mode (de-scoped?) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N
105 | • Bridge mapping mode (de-scoped?) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N
106 | • IP Host capability (de-scoped?) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N
107 | • DSCP to PBIT functionality (ONT or OLT) (de-scoped) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N
108 | • Data Dump Information (enabled, date, time) (de-scoped?) | Onu Management | descope | L | L |  | Y | N/A | N/A | Y |  |  | N
109 | 5.7.4 Retrieve Operational ONT Parameters
110 | • PLOAM status (Loss of signal, Signal degrade, Signal Fail, Dying Gasp, ) | Alarms |  | H | H1 | This was split into gating alarms vs not gating alarms | Y | ? | ? | Y |  |  | N | Stretch | Y | BAL support !!!!!!! |  | Non-EdgeCore OLT
111 | • PLOAM status (Loss of signal, loss of acknowledgement, loss of GEM channel delineation, Physical Equipment Error, Start-up failure, Signal degrade, ONT disabled, Inactive, Loss of Frame, Signal Fail, Dying Gasp, Deactivation Failure, Loss of PLOAM, Window drift, Remote Defect Indicator, Loss of Key Sync, Differential Reach Exceeded) | Alarms |  | H | H3 | Some of the PLOAM alarms are less likely to happen | Y | ? | ? | Y |  |  | N | Stretch | Y | The ? Need to be updated |  | Non-EdgeCore OLT
112 | • Distance (estimation) between OLT and ONT | Pon Management |  | M |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
113 | • 802.1x – Report both PAE (initialized, disconnected, connecting, authenticating, authenticated, aborting, held, forced (auth and unauth) and backend (request, response, success, fail, timeout, held, initialize) states. Counters for each of these should be available. | Control Plane |  | M? | M |  | Y | N/A | N/A | N |  |  | Y | Stretch | Y |  |  | Non-EdgeCore OLT
114 | 5.7.5 Retrieve ONT optical parameters
115 | • ONT TX and RCV levels (and associated TCAs for High and Low alarms) | Onu Management |  | M | L | I would consider TCAs as advanced functionality. | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
116 | • OLT RCV level | Onu Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
117 | • Temperature | Onu Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
118 | • Voltage | Onu Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
119 | • Laser bias current | Onu Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
120 | • These parameters should be able to be logged for historical data pulls | Onu Management |  | L |  |  | Y | ? | ? | Y |  |  | N | Stretch | Y |  |  | Non-EdgeCore OLT
121 | 5.7.6 Retrieve Alarms
122 | • On all provisioned equipment (vOLT, ONOS, vOLTHA, NNIs, LAGs, PONs, ONTs, UNIs, HSIA Services, POTS/VoIP services, configured VLANs, PMAAs) | Alarms |  | H | H1 | Here we need to look at specific alarms to decide which ones are critical | Y | ? | ? | Y |  |  | Y | Stretch | Y | harmonizing Alarm |  | Non-EdgeCore OLT
123 | • Severity level indication (Critical, Major, Minor…depending on service affecting) | Alarms |  | H | M | This is marked as M in 11 [Ying - I splitted 11 into 2 req] | Y | ? | ? | Y |  |  | N | Stretch | Y | The ? Need to be updated |  | Non-EdgeCore OLT
124 | 5.7.7 Retrieve System CPU Utilization
125 | • Current and average system load (Device, VOLTHA, ONOS, etc.) | System Management |  | L | L | Should be rather easy to look using esiting system commands | Y | ? | ? | Y |  |  | Y | Stretch
126 | 5.7.8 Retrieve RADIUS Information
127 | • Domain IS, OOS | Control Plane | descope | N/A | N/A | These is not relevant to D2. These are taken from legacy implementation and are not relevant for the “aaa” app in ONOS. | Y | N/A | N/A | N |  |  | Y | N/A | N/A |  |  | N/A
128 | • Domain Policy | Control Plane | descope | N/A | N/A | These is not relevant to D2. These are taken from legacy implementation and are not relevant for the “aaa” app in ONOS. | Y | N/A | N/A | N |  |  | Y | N/A | N/A |  |  | N/A
129 | • Auth Server IS, OOS | Control Plane |  | L | L | This is used to determine if the radius server is down. Since Radius uses UDP, a special mechanism is to be deviced to determine if Radius server is down. Is this critical for Field trial? IMHO, may be not? | Y | N/A | N/A | N |  |  | Y | Stretch | Y
130 | • Auth Server IP:port | Control Plane |  | H | H1 | Already supported, i.e. configuration of authentication server and port. Is required since in Ph-2, the auth server used the old Radius port. | N | N/A | N/A | N |  |  | N | Stretch | Y
131 | • Auth Server retry, timeout parameters | Control Plane |  | M | L | Configurable retries are low priority wrt others. | Y | N/A | N/A | N |  |  | Y | Stretch | Y
132 | 5.7.9 Retrieve Equipment
133 | • Current provisioned equipment | Device Management |  | H | H1 |  | N | Done | Done | N |  |  | N | Y
134 | • IS, OOS | Device Management |  | H | H1 |  | N | Done | Done | N |  |  | N | Y
135 | 5.8 Interoperability
136 | • Operate as many different (foreign) ONUs on as many different OLTs as is practical | Interop |  | H | H3 |  | Y | VOL-127 | VOL-127 | Y |  |  | N | Stretch | Y |  |  | ALL OLT
137 | • Compute Portability – Validate the Solution does not have any dependencies on particular types of hardware, and/or document any dependencies identified. | Interop |  | H | H1 |  | Y | Done | Done | Y |  |  | Y | Y |  |  |  | VOLTHA
138 | • Interoperability with CPE equipment (Arris 589/599 and Pace 5268 at beginning via media converter) | Interop |  | L |  |  | Y | N/A | N/A | N |  |  | N | N/A | N/A | HW |  | ALL OLT
139 | • OpenOMCI (Stretch goal) | Interop | Unknown | L |  |  | Y | VOL-127 | ? | Y |  |  | N | Stretch | Y |  |  | ALL OLT
140 | 5.9 Operational/Support/Debug Tools
141 | • ONT self-test functionality | Onu Management |  | L |  |  | Y | ? | ? | Y |  |  | N | N/A | N/A | HW/FW |  | ALL OLT
142 | • Edit an ONT IS/OOS | Device Management |  | H | H1 |  | Y | VOL-7 | ? | Y |  |  | N | Y |  |  |  | ALL OLT
143 | • Assign/Unassign Serial numbers to ONTs | Onu Management |  | H | H1 |  | Y | VOL-7 | ? | Y |  |  | N | Y |  |  |  | ALL OLT
144 | • Delete ONTs (withouot restarting VOLTHA) | Onu Management |  | H | H1 |  | Y | VOL-7 | VOL-93 | Y |  |  | N | Y |  |  |  | ALL OLT
145 | • Download/Activate Software and retrieve active SW version | Onu Management |  | H | H3 |  | Y | VOL-133 | VOL-63 | Y |  |  | N | Stretch | Y |  |  | ALL OLT
146 | • LED Status Indicator accuracy and usability | Onu Management |  | M |  |  | N | N/A | N/A | N |  |  | N |  |  | HW/FW |  | ALL OLT
147 | 5.10 Layer-1 Compliance
148 | • Verify Industry Standards Compliance | Compliance |  | H | H1 |  | N | N/A | N/A | N |  |  | N |  |  | Repeat Ph 1 & 2 |  | ALL OLT
149 | • G.989, G.989.1, G.989.2, G.989.3 | Compliance |  | H | H1 |  | N | N/A | N/A | N |  |  | N |  |  | Repeat Ph 1 & 2 |  | ALL OLT
150 | • G.988 – ONU Management and Control Interface (OMCI) | Compliance |  | H | H1 |  | N | Done | Done | N |  |  | N |  |  | Repeat Ph 1 & 2 |  | ALL OLT
151 | • BBF TR-156 | Compliance |  | H | H1 |  | N | N/A | N/A | N |  |  | N |  |  | Repeat Ph 1 & 2 |  | ALL OLT
152 | • BBF TR-247 ONU Conformance Test | Compliance |  | M |  |  | N | N/A | N/A | N |  |  | N |  |  | Repeat Ph 1 & 2 |  | ALL OLT
153 | • Establish communication/range between the OLTs and ONT | Compliance |  | H | H1 |  | N | N/A | N/A | N |  |  | N |  |  | Repeat Ph 1 & 2 |  | ALL OLT
154 | • Optical Loss/Budget Testing – Test ONT’s ability to operate throughout its “window” | Compliance |  | H | H1 |  | N | N/A | N/A | N |  |  | N |  |  | Repeat Ph 1 & 2 |  | ALL OLT
155 | 5.11 Functional Testing
156 | • RADIUS for RG/Subscriber authentication (802.1x Authentication against Operator Lab standard RADIUS with Operator provided RGs is required) | Control Plane |  | N/A | H1 |  | N | N/A | N/A | N |  |  | N |  |  | ONOS Code Merge |  | ALL OLT
157 | • DHCP | Control Plane |  | N/A | H1 |  | N | N/A | N/A | N |  |  | N |  |  | ONOS Code Merge |  | ALL OLT
158 | • Multicast (4 and 6 simultaneous streams of HD with ICC support) | Control Plane |  | N/A | H1 |  | N | N/A | N/A | N |  |  | N |  |  | ONOS Code Merge |  | ALL OLT
159 | • TR-69 management of RGs by CMS | Services |  | N/A |  |  | Y | N/A | N/A | N |  |  | N |  |  |  |  | ALL OLT
160 | • ONT remote reboot. Remote enable ONT | Device Management |  | H | H1 |  | Y | VOL-7 | VOL-57 | Y |  |  | N | Y |  |  |  | ALL OLT
161 | • OLT reboot. Remote enable OLT | Device Management |  | H | H1 |  | Y | VOL-7 | VOL-27 | Y |  |  | N | Y |  |  |  | ALL OLT
161 | 5.12 Integration-Level Items
162 | • Verify OLT system is inventoried/recognized by VOLTHA | Entity Management |  | M |  |  | Y | VOL-7 | VOL-47 | Y |  |  | N | Stretch | Y | Not impacting the Ph3 |  | ALL OLT
163 | • Verify OLT is capable of being managed by VOLTHA | Entity Management |  | M | H | Ying - How so? | N | VOL-7 | VOL-47 | Y |  |  | N | Stretch | Y | Not impacting the Ph3 |  | ALL OLT
164 | • Capable of “on demand” management task recognition (i.e. reboot, profile change, RSSI,inventory query response, debug, etc.) | Onu Management |  | M | M | Reboot is covered by 166. The rest of the items are not critical for field trial IMHO [Ying - OK, but make sure 166 will be delivered] | Y | ? | ? | Y |  |  | N | Stretch | Y
165 | • Demonstration of the alarm/event configuration capability, including configuring alarm severity, alarm supression, alarm acknowledge and clearing with vOLT software. | Alarms |  | M |  |  | Y | ? | ? | Y |  |  | N | Demo in ph3 | Y
166 | o Review the current supported alarm/event list. | Documentation |  |  | Doc |  | N | VOL-3 | VOL-3 | Y |  |  | N | Doc |  | HW dependant |  | ALL OLT
167 | • Demonstration of OLT software download capability | SW & Image Management |  | M | M | This is about being able to support device(OLT) SW upgrades. I think in my view, some sort of mechanism is necessary, it does not necessarily have to be via vOLT to start with but we need to have some mechanism to upgrade device SW | Y | VOL-133 | VOL-63 | Y |  |  | N | Demo in ph3
168 | o At the minimal, provide the proposal about how to utilize the vOLT SW component to upgrade the OLT/ONT SW. | SW & Image Management |  | M | M | See 174 | Y | VOL-133 | VOL-63 | Y |  |  | N | Stretch | Y
169 | o What interface and application in VOLTHA framework will provide this functionality? | Documentation |  |  | Doc |  | N | VOL-3 | VOL-3 | Y |  |  | N | Stretch | Y
170 | • Verify PON operations act such that the behavior and operation of new ONTs is not disruptive and transparent/contiguous with that of currently deployed units. Examples include: Software downloads to ONT groups. | Resiliency |  | M |  |  | N | N/A | N/A | N |  |  | N
171 | • Verify vOLT is not disruptive with existing QoS policies/implementations and allows for transparent application of current service configurations. Queuing structures and other QoS configurations should allow for seamless service provisioning and QoS execution. (Perhaps future test?) | Resiliency |  | L |  |  | N | N/A | N/A | N |  |  | N
172 | 5.13 Security
173 | • SPR (Security Policy Requirement) | Security |  | M | L | I remember that we dicsussed this during the TST meetings and vaguely remember hearing that ASPR compliance is low priority for Field trial | Y | VOL-11 | VOL-11 | Y |  |  | Y |  | Y
174 | • Security requirements (lpriviledged command segregation) | Security |  | H | H3 | Field trial will be in Operator controlled environment. | Y | VOL-128 | VOL-128 | Y |  |  | Y | Y
175 | • Security requirements (least priviledge principle) | Security |  | H | H3 | Field trial will be in Operator controlled environment. | Y | VOL-129 | VOL-129 | Y |  |  | Y | Y
176 | • Security requirements (user accounts, no hardcodedpasswords) | Security |  | H | H3 | Field trial will be in Operator controlled environment. | Y | ? | ? | Y |  |  | Y | Y
177 | • userid/passwd for sub-components | Security |  | H | H3 | Field trial will be in Operator controlled environment. | Y | ? | ? | Y |  |  | Y | Y
178 | 5.15 Creation and Validation of Deployable Software Images
179 | • Installation images in the form of tar or equivalent shall be created and validated during Phase-3. | SW & Image Management |  | Gating |  |  | Y | VOL-6 | VOL-6 | Y |  |  | Y | Y
180 | • Software distribution (strict version control, release numbers, hashed and signed) | SW & Image Management |  | Gating |  |  | Y | VOL-6 | ? | Y |  |  | Y | Y
181 | 5.xx Support for EdgeCore HW Variant
182 | • Generic Adapter in VOLTHA with EdgeCode OCP HW | Generic Adapter |  | H | H3 | Priority provided wrt availability | Y | VOL-130 | VOL-130 | Y |  |  | Y | Y |  |  |  | EdgeCore
Note on E48: Ying, Shawn: Should already be there
Note on E49: Ying, Shawn: Should already be there
Note on E50: Ying, Shawn: Should already be there
Note on E51: Ying, Shawn: Should already be there
Note on E52: Ying, Shawn: Should already be there
Note on E53: Ying, Shawn: Should already be there
Note on E58: Ying, Shawn: Should already be there
Note on E65: Ying, Shawn: Should already be there
Note on S118: Ying, Shawn: BAL supports it
Note on S119: Ying, Shawn: BAL supports it
Note on S120: Ying, Shawn: BAL supports it
Note on S121: Ying, Shawn: BAL supports it
Note on S123: Ying, Shawn: BAL supports it
Note on S124: Ying, Shawn: BAL supports it
Note on S125: Ying, Shawn: BAL supports it
Note on S126: Ying, Shawn: BAL supports it
Note on S127: Ying, Shawn: BAL supports it
Note on S128: Ying, Shawn: BAL supports it
Note on S130: Ying, Shawn: BAL supports it
Note on S131: Ying, Shawn: BAL supports it

## Documentation and Process
Requirement | Priority | Epic
Product Evaluation Agreement |  | N/A
Solution-Set Matrix |  | N/A
Checklist / Statement of Confirmance (1 week prior) |  | N/A
System-Level Configuration (in advance for review) |  | VOL-3
Internal test cases, test scripts and test reports |  | ?
CLI command guide and configuration guides |  | VOL-3
Product manuals and user guides |  | VOL-1
Scalability - initial outlook and verification document (dimensions, througput, how to test) |  | ?
Compute requirements (minimum RAM, CPU cores, disk space, etc.) |  | ?
Installation (document commands requiring elevated privileges) |  | VOL-2
Commisioning procedure and criteria |  | ?
Multi-Vendor Test (booking opens 5/22, starts 5/30) |  | N/A
Support Plan (contacts and infrastructure) |  | N/A